## Project Plan
PROJECT PLAN
PHASE AND STEP | HOURS | RESOURCE | COMPLETE DATE
PHASE I: Preparation for Implementation | 8
Plan Resources | 1.5
Identify project champion | 0.5
Form implementation team | 1
Conference Call - Project Team and Datanet Project Mgr | 1
Confirm project objectives and success metrics | 0.25
Discuss resources required and timelines | 0.25
Review training options | 0.25
Determine system requirements | 0.25
Hardware (Allocate or Purchase) | 5.5
Server hardware | 1
Client hardware (plant floor PCs) | 2
Network hardware | 1
Gage hardware (cables, flexports, etc.) | 1.5
PHASE II: Installation, Training, Configuration and Pilot | 40
Database | 1
Install database server software | 0.5
Configure database server for WinSPC | 0.5
Installing WinSPC | 3
Install WinSPC on the first client station | 1
Install WinSPC on all other client stations | 2
Orientation for WinSPC Solutions Engineer | 1
Plant walk through explaining processes | 0.5
Overview of inspection plans and SPC methods | 0.5
Onsite WinSPC Training | 24
Setup training room | 3
Conduct WinSPC admin training | 16
Conduct WinSPC operator training (group format) | 1
SPC Fundamentals training | 4
General Security and System Configuration | 3
Define WinSPC configuration structure | 1
Create user groups and users | 0.75
Grant user permissions | 0.5
Configure language, audit trail, event log, etc. | 0.75
Conduct Pilot | 8
Identify pilot operation (i.e. operation 1) | 0.25
Setup 1-5 parts | 0.5
Setup variables and attributes for each part | 0.5
Setup tags | 0.25
Setup blueprint images | 0.25
Setup cost model | 0.75
Copy setup for other operations as appropriate | 0.25
Setup 1-5 sample collection plans | 0.25
Setup blueprints | 0.25
Setup tag prompting | 0.25
Setup device prompting | 0.25
Link appropriate files to Navigator buttons | 0.25
Setup devices within WinSPC | 0.5
Setup sample plant monitor layout | 0.25
Create lists (N, CA, AC) | 0.5
Link (or apply) lists | 0.25
Define alarms and triggers | 0.25
Create control test templates | 0.25
Link (or apply) control test templates | 0.25
Setup sample queries and reports | 0.5
Collect data | 0.5
Obtain user feedback | 0.25
Modify setup as needed | 0.25
Collect more data to confirm modified setup | 0.25
PHASE III: Deployment to All Other Operations | 80
Operation 2 | 4
Operation 3 | 4
Operation 4 | 4
Operation 5 | 4
Operation 6 | 4
Operation 7 | 4
Operation 8 | 4
Operation 9 | 4
Operation 10 | 4
Operation 11 | 4
Operation 12 | 4
Operation 13 | 4
Operation 14 | 4
Operation 15 | 4
Operation 16 | 4
Operation 17 | 4
Operation 18 | 4
Operation 19 | 4
Operation 20 | 4
Operation 21 | 4
PHASE IV: Go Live | 112
Roll out WinSPC to all stations | 72
Document instructions for using WinSPC | 16
Fine-tune setup based on user feedback | 16
Document and share lessons learned | 8
PHASE V: Ongoing Monitoring | Ongoing
Monitor programs and usage of WinSPC | Ongoing
Review success of WinSPC deployment at facility | Ongoing
Review success metrics (ongoing) | Ongoing
|  | Total Hours | 240
|  | Total Days | 30